## OOA1-bud-mike-work
RBM Example of Output-bases Budget
Typical budget lines | Human Resources |  |  |  | Monitoring & Evaluation |  |  |  | Training
| Travel |  |  |  | Research Supplies
| Equipment |  |  |  | Office Materials
| Proj. Mgmt. (PMC) |  |  |  | Dissemination
| Stakeholder Engagement |  |  |  | Subcontracting and Services
Item |  |  |  | OUTPUT
Human Res. | % Tot. time | Category | % for category | 1110 | 1120 | 2110 | 21200 | 2130 | 3110 | 3120 | 3130 | Tot. | Tot. Sal. (% of time)
Researcher 1 | If more than one country … | Proj Mgt. | 0.3 |  | 0.1 | 0.1 |  |  | 0.1 |  |  | 0.3 | 0.3 | 100000 | #VALUE!
|  | Theses | 0.15 | 0.05 |  |  | 0.05 |  |  | 0.05 |  | 0.15 | 0.15
|  | Analytical | 0.15 |  | 0.05 | 0.05 |  | 0.05 |  |  |  | 0.15 | 0.05
|  | Reporting | 0.1 | 0.1 | [7 empty] | 0.1 | 0.1
|  | Research | 0.1 | [5 empty] | 0.1 |  |  | 0.1 | 0.15
|  | Publication | 0.2 |  | 0.1 | [5 empty] | 0.1 | 0.2 | 0.1
|  |  | 1 | 0.15 | 0.25 | 0.15 | 0.05 | 0.05 | 0.2 | 0.05 | 0.1 | 1 | 0.1
|  |  | $ | 15000 | 25000 | 15000 | 5000 | 5000 | 20000 | 5000 | 10000 | 100000 | 1 | 100000
Researcher 2 |  | Field Work | 0.5 |  |  |  | 0.25 |  | 0.25 |  |  | 0.5 |  | 80000
|  | Lab Protoc. | 0.2 |  | 0.1 |  |  | 0.1 |  |  |  | 0.2
|  | Train Stud. | 0.3 | 0.1 |  | 0.1 |  |  |  | 0.1 |  | 0.3
|  |  | 1 | 0.1 | 0.1 | 0.1 | 0.25 | 0.1 | 0.25 | 0.1 | 0 | 1
|  |  | $ | 8000 | 8000 | 8000 | 20000 | 8000 | 20000 | 8000 | 0 | 80000
80000
Travel |  | Intern. | 0.25 | 0.05 |  | 0.05 |  | 0.05 |  | 0.1 |  | 0.25 |  | 50000
|  | National | 0.5 | 0.2 | 0.1 |  | 0.05 | 0.05 | 0.05 | 0.05 |  | 0.5
|  | Regional | 0.2 | 0.1 | [6 empty] | 0.1 | 0.2
|  | Local | 0.05 | 0.05 | [7 empty] | 0.05
|  |  | 1 | 0.4 | 0.1 | 0.05 | 0.05 | 0.1 | 0.05 | 0.15 | 0.1 | 1 | 1
|  |  | $ | 20000 | 5000 | 2500 | 2500 | 5000 | 2500 | 7500 | 5000 | 50000 |  | 100000
Equipment |  | Inst. #1 | 0.5 |  |  | 0.5 | [5 empty] | 0.5 |  | 150000
|  | Inst. #2 | 0.25 |  |  |  |  | 0.25 |  |  |  | 0.25
|  | Inst. #3 | 0.25 | [5 empty] | 0.25 |  |  | 0.25
|  |  | 1 | 0 | 0 | 0.5 | 0 | 0.25 | 0.25 | 0 | 0 | 1
|  |  | $ | 0 | 0 | 75000 | 0 | 37500 | 37500 | 0 | 0 | 150000 |  | 300000
SUMMARY INFORMATION FOR CALCULATING VARIANCE
REPORTING PERIOD |  |  |  | OUTPUT
TO DATE |  |  |  | 1100 | 1200 | 2100 | 2200 | 2300 | 3100 | 3200 | 3300 |  | SUB-T
Salaries |  |  |  | 23000 | 33000 | 23000 | 25000 | 13000 | 40000 | 13000 | 10000 |  | 180000
Travel and Subsistence |  |  |  | 20000 | 5000 | 2500 | 2500 | 5000 | 2500 | 7500 | 5000 |  | 50000
Analytical
Equipment
Research
Material & Supplies
Capacity building
Dissemination
Indirect Costs
Subcontracting and Services
To date total by output |  |  |  | 43000 | 38000 | 25500 | 27500 | 18000 | 42500 | 20500 | 15000
Salaries
Travel and Subsistence
Research
Equipment
Analytical
Material & Supplies
Capacity building
Dissemination
Indirect Costs
Subcontracting and Services
5 year total by output |  |  |  | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx |  | XXX
Variance by Output |  |  |  | -0.27816 | -0.29931 | -0.30483 | -0.43372 | -0.29777 | -0.3001 | -0.30053 |  |  | -0.3008

## Planned Results, 100-110
India Sludge Project: Summary of Planned Results for the Project and First Period (2002/2003)
Expected Results of Outcome # 100: 20 sewage treatment facilities inventoried for volume of sludge produced; volume of sludge supplied to local farmers determined; chemical/physical properties of sludge determined at all facilities
|  |  | Expected Results for Life of Project | Results Planned for Upcoming Period | Actual Results | Variance of Planned to Actual | Progress Towards Results to Date
Activity as % of Total Output | Portion of Activity Completed during period | % of Output Completed | Planned Output # 110: Producers and Users of Sludge Identifies and Linkages with all Partners Established | 85% of weighted activities completed
3 | 1 | 3 | Planned Activity #111: Establish headquarters of Canadian Proj. team | Headquarters established
2 | 1 | 2 | Planned Activity #112: Purchase and install all office equipment | Equipment purchased, installed and operational
20 | 1 | 20 | Planned Activity #113: Undertake reconnaisance field work to identify sludge facilities | 20 Treatment plants selected for study
25 | 0.44 | 11 | Planned Activity #114: Identify and establish relations with farmers using sludge at the 20 study sites | All users identified at 20 sites and relationships established with 50%
5 | 0.88 | 4.4 | Planned Activity #115: Determine demographics of villages using sludge | Complete demographic surveys for 50% of identified users
30 | 1 | 30 | Planned Activity #116: Contact local NGOs and finalize MOU's | All NGOs identified and MOUs established with as many as possible
15 | 1 | 15 | Planned Activity #117: Identify and enlist support of all potential partners | All partners contacted and informed of project activities
100 |  | 85.4
BASIS FOR RESULTS VARIANCE
Note on B8: Mike Powell: see e8
Note on E8: Mike Powell: identifying = 25% of the total relationships = 75% of total ((.25)(.25))+((.75)(.5))= 0.4375
Note on D9: Mike Powell: lead time required to design surveys and contact NGOs. The other 50% will go faster in year 2
Note on E9: Mike Powell: design = 75% administering = 25% ((1)(.75)+(.5)(.25)=0.88

## Planned Results, 100-130
Annexure 5.A
India Sludge Project: Summary of Planned Results for the Project and First Period (2002/2003
Expected Results of Outcome # 100: 20 sewage treatment facilities inventoried for volume of sludge produced; volume of sludge supplied to local farmers determined; chemical/physical properties of sludge determined at all facilities
|  |  | Expected Results for Life of Project | Results Planned for Upcoming Period | Actual Results | Variance of Planned to Actual | Progress Towards Results to Date
Activity as % of Total Output | Portion of Activity Completed during period | % of Output Completed | Planned Output # 130: Chemistry, microbiology and toxicology of sewage sludge evaluated. | 45% of Weighted activities completed
5 | 1 | 5 | Planned Activity 131: Establish Lab protocols | All lab protocols established
50 | 0.67 | 33.5 | Planned Activity 132: Prepare and split 600 samples for various analytical methods | 400 samples prepared for analyses
5 | 0.67 | 3.35 | Planned Activity 133: Send representative samples to appropriate labs | 400 samples sent for analyses
20 | 0 | 0 | Planned Activity 134: Compile, reduce, evaluate data | None
10 | 0.6 | 6 | Planned Activity 135: Train 9 Indian staff in appropriate lab techniques (technical and development) | 6 staff trained
10 | 0 | 0 | Planned Activity 136: Determine application rates | None
100 |  | 47.85
BASIS FOR INDICATORS
Note on D7: Mike Powell: Mike has given an $810,000 budget sludge: (20 facilities)(10 samp./fac.) = 200 samples each for 3 years = 600 total Soil: (200 farms)(5 samp./farm) = 1000 samples each for 3 years = 3000 total Vegetation: (200 farms)(5 samp./farn)(2 parts/veg) = 2000 each for 3 years = 6000 sludge: ($175 tox)+($50 geo) = 225. for 600 samples = 135,000 soil: (1000 samp)($150 tox) = 150,000 (3000 samp.)($75 geochem.) = 225,000 plants: (6000 samp.)($50 aq regia) = 300,000 Total budget = 810,000
Note on D10: Mike Powell: Training: field collection, lab treatment, packing, preparation for analyses At IIT-Kanpur and U. Allahabad we will need staff Staff at Kanpur are sociologists (students rather than JPOs) = 3 (15,000/mo for the JPO)+(5,000/mo for each of 2 students)(5 yrs)15,00,000 (this is 15 lahk) or $50,000 @ $1 = Rs30. Therefore, $25,000 left for equip, etc. (note 1 trip.year aslo for each person to Canada) Staff at Allahabad are geochemists = 3 (same rationale as Kanpur) Staff at IIT Kharagpur = 3 Total of 9 staff

## OOA-output report-final
THIS WORKSHEET IS PROVIDED FOR INTERNAL USE BY PROJECT STAFF TO CALCULATE RESULTS AND BUDGET VARIANCE FOR EACH OUTPUT FOR USE AS REQUIRED IN OTHER REPORTING DOCUMENTS
Output Budget ($)1 | Activity as Weighted Fraction of Total Output2 | Reporting Period Anticipted Result (Activity)3 | Reporting Period Achieved Result (Activity) | Planned Activity Budget ($) | Spent Activity Budget ($) | Weighted Fraction of Activity Achieved for Reporting Period | Weighted Fraction of Output Achieved for Reportig Period | Fraction of Output Achieved to Last Reporting Period | Fraction of Output Achieved to date | Fraction of Output Budget Spent for Reporting Period | Output Budget Spent to Last Reporting Period | Output Budget Variance to Date
100 | 0.2 | 20 | 10 | 20 | 10 | 0.1 | 0.26667 | 0.25 | 0.51667 | 0.5 | 0.25 | 0.75
| 0.2 | 10 | 1 | 20 | 10 | 0.02
| 0.2 | 5 | 2 | 20 | 10 | 0.08
| 0.2 | 2 | 0 | 20 | 10 | 0
| 0.2 | 15 | 5 | 20 | 10 | 0.066667
1 From Sheet "OOA1-output-final" 2xx 3From Sheet "OOA1-activity-final"
THIS WORKSHEET IS PROVIDED FOR INTERNAL USE BY PROJECT STAFF TO CALCULATE RESULTS AND BUDGET VARIANCE FOR EACH OUTCOME FOR USE AS REQUIRED IN OTHER REPORTING DOCUMENTS
Outcome Budget ($)1 | Output as Weighted Fraction of Total Outcome2 | Reporting Period Anticipted Output Result3 | Reporting Period Achieved Output Result | Planned Outcome Budget ($) | Spent Outcome Budget ($) | Weighted Fraction of Outcome Achieved for Reporting Period | Weighted Fraction of Outcome Achieved for Reportig Period | Fraction of Outcome Achieved to Last Reporting Period | Fraction of Outcome Achieved to date | Fraction of Outcome Budget Spent for Reporting Period | Outcome Budget Spent to Last Reporting Period | Outcome Budget Variance to Date
[6 empty] | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! |  | #DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
1 2 3
HOW ???

## OLD OUTCOME 100
LAND RESTORATION THROUGH WASTE MANAGEMENT (IIT-ICEF) AND MULTIPURPOSE WASTE RECYCLING (UWO-CIDA) | [5 empty] | LAND RESTORATION THROUGH WASTE MANAGEMENT (IIT-ICEF) AND MULTIPURPOSE WASTE RECYCLING (UWO-CIDA) | [8 empty] | LAND RESTORATION THROUGH WASTE MANAGEMENT (IIT-ICEF) AND MULTIPURPOSE WASTE RECYCLING (UWO-CIDA)
LFA BASED JOINT TECHNICAL REPORTING FORMAT | [5 empty] | LFA BASED JOINT TECHNICAL REPORTING FORMAT | [8 empty] | LFA BASED JOINT TECHNICAL REPORTING FORMAT
OUTCOME NUMBER: |  | #100 |  |  |  | OUTCOME NUMBER: |  | #100 | [6 empty] | OUTCOME NUMBER: |  | #100
REPORTING PERIOD: |  | SEPT/00-MAR/01 |  |  |  | REPORTING PERIOD: |  | SEPT/00-MAR/01 | [6 empty] | REPORTING PERIOD: |  | SEPT/00-MAR/01
[6 empty] | OUTPUT LEVEL |  | UWO/IIT - JOINT ACTIVITIES | [6 empty] | SUMMARY
| OUTCOME LEVEL | OUTPUT LEVEL | [5 empty] | REPORTING PERIOD |  |  | TOTAL ACHIEVED TO LAST PERIOD | TO DATE |  |  |  | UWO/IIT JOINT BUDGET | [5 empty] | TO DATE ACTIVITY
| NARRATIVE STATEMENT | OUTPUT | EXPECTED RESULTS OVER THE LIFE OF THE PROJECT | PROGRESS TOWARDS RESULTS TO DATE | VARIANCE |  | ACTIVITY | PLANNED | ACHIEVED | VAR. |  | PLANNED | ACHIEVED | VAR. |  | AS END OF LAST REPORT (SEPT/00) |  |  | TO DATE
|  |  |  | ACHIEVED | VARIANCE | [11 empty] | SPENT | TO DATE VAR. | ALLOC. (5-Year) | SPENT | VAR. | VARIANCE
100 FEASIBILITY OF TECHNOLOGY DEMONSTRATED | The feasibility of the technology has been demonstrated on 362 Ha of trees. An additional 3 Ha of edible crop trials have been established. The trees planted in the mixtures are producing more biomass than the controls, the survival rate is considerably higher than traditional methods (90+% vs 40%, in sojme cases) and the local environs withing plantations (between trees) are showing marked improvement (grasses). Large volumes of fuelwood and fodder are being supplied at some plantation sites. Two private sector organizations (MP and AP) have adopted some part the technology on their own after either hearing about or seeing project work. The Govt. of Orissa, City of Cuttack, has entered into an agreement to implement the work at shared cost with the project - they are supplying land, seedlings, sludge and ash for approx. 100 Ha. The Govt. of Rajasthan has issued an order to try the technology in villages in the vacinity of Kota, but no activity has taken place to date. | 110 TECHNICAL FEASIBILITY DEMONSTRATED IN FOUR AGRO-CLIMATIC ZONES | 14 tree sites (total of 399 Ha) are planned in 5 states with varying agroclimatic and soil conditions: UP, 2 sites, 57 Ha; MP, 5 sites, 107 Ha; AP, 3 sites, 100 Ha; OR, 3 sites, 110 Ha; RA, 1 site, 35 Ha. In addition, 3 edible crop sites are planned: MA, 1 site, 1 Ha; KA, 1 site, 1 Ha; WB, 1 site, 1 Ha. | Plantation at Cuttack with CMC as the implementing agency was initially planned to be executed over 100ha and the budget was worked out accordingly. In the first year, 60ha was planted and another 10ha was also made ready for plantation ie pit digging was complete. Plantation was established over 10ha during this reporting period along with another 30ha as an extension plantation. The funding agency has recommended stopping all project related activities at Rajastahn since the schedule for plantation has been disrupted and at this point of time cannot be completed by the present duration of the project ie March 2002. Rajasthan Govt. and all the others concerned have been informed. The existing plantations are however being asked to be maintained. Experiments in the 3 edible crop trial sites have been stopped. | Tree sites, -7% Edible sites, 0% | OUTPUT 110 | 111 PRE-PLANTATION ACTIVITIES | None | None | 0% | 399 Ha trees; 3 Ha edible | 399 Ha trees; 3 Ha edible | 399 Ha trees; 3 Ha edible | 0% | OUTPUT 110 |  | 709177 | -28% | 982452 | 773797 | -21% | Tree, -7% Edible, 0%
[7 empty] | 112 TECHNICAL BASELINE DATA COLLECTED | Baseline tree sites - soil samples, sludge and ash: OR, 2 sites (110 Ha); UP, 1 site (7 Ha) | OR: 110 Ha collected. UP: included in previous samples | 0% | 399 Ha trees; 3 Ha edible | 399 Ha trees; 3 Ha edible | 399 Ha trees; 3 Ha edible | 0%
[7 empty] | 113 PLANTATIONS ESTABLISHED | 0 | 0 | 0% | 372 Ha tree: 3 Ha edible | 399 Ha trees; 3 Ha edible | 372 Ha tree: 3 Ha edible | Tree, - 7% edible, - 0%
[7 empty] | 114 TREE PLANTAIONS MAINTAINED | 14 tree sites | 13 tree sites | -7% | 13 tree sites | 14 tree sites | 13 tree sites | Tree, - 7%
[7 empty] | 115 CROP TRIALS MAINTAINED | 3 crop sites | 3 crop sites | 0% | 3 crop sites | 3 crop sites | 3 crop sites | 0%
[7 empty] | 116 TECHNICAL MONITORING | 13 tree sites | 13 tree sites | 0% | 13 tree sites, 3 edible | 14 tree sites, 3 edible | 13 tree sites, 3 edible | Tree, -7, edible, 0%
|  | 120 ECONOMIC AND FINANCIAL FEASIBILITY DEMONSTRATED | The cost of using the technology is more expensive than "traditional" methods. Demonstrating to the private and public sectors that using the technology adds value to waste materials is key to replication. | Economic cost benefit analysis is expected to be completed by end of 2001. Consultant for carrying out this work has been identified and the process in under progress. | Estimated, -75% | OUTPUT 120 | 121 STUDY OF FINAN. FEAS. IN PRIV. SECTOR | 1 (KITPLY) | 1 (KITPLY) | 0% | 1 | 0 | 0 | NA | OUTPUT 120 |  | 18651 | -30% | 26618 | 26618 | -20% | Estimated -75%
[7 empty] | 122 ECON. COST-BEN. ANAL. OF WASTELAND RECLAMATION | See Narrative | See Narrative | NA | See Narrative | See Narrative | See Narrative | NA
[7 empty] | 123 POLICY INPUTS ON WASTE UTIL. FOR WASTELAND DEV. | See Narrative | See Narrative | NA | See Narrative | See Narrative | See Narrative | NA
|  | 130 TECHNOLOGY DISSEMINATED AND PROMOTED TO ALL SECTORS | A dissemination plan, and course of action, were discussed during the MTPA, March/2000. There was no formal/written plan included in the project until that time. The plan will be formulated by consultants in India and will include a plan to disseminate information (mailings, etc.), 1 national workshop, 2-3 regional workwhops (information sessions) and outreach meetings by partner NGO's. The dissemination plan (by consultants) is expected to be completed in the 2nd quarter, 2000; workshops are planned for the 2nd and 3rd quarters, 2001. Meetings/conferences will be attended by project staff when possible. | Dissemination and communication plan for the use of fly ash and sewage sludge in wasteland remineralization through plantations has been developed. The report has been received and evaluated. It has been decided to have a website developed, 2000 brochures printed and hold 2 workshops for dissemination at Delhi and Bhubaneshwar.Two abstracts regarding the socio economic aspect of the project have been submitted to international conferences | Estimated, -80% | OUTPUT 130 | 131 FORM. OF DISS./COMM. PLAN BY EXT. CONS. | See Narrative | See Narrative | NA | See Narrative | See Narrative | See Narrative | NA | OUTPUT 130 |  | 101520 | -30% | 146037 | 116239 | -20% | Estimated -80%
[7 empty] | 132 NATIONAL WORKSHOPS | 0 | 0 | NA | 0 | 3 | 0 | -100%
[7 empty] | 133 OUTREACH BY PARTNER NGO'S | See Narrative | See Narrative | NA | See Narrative | See Narrative | See Narrative | NA
[7 empty] | 134 CONFERENCES, PROCEEDINGS, MEETINGS | Scientific: 3 | Scientific: 3 | 0% | Scientific: 8. General (India) 2 | 0 | 13 | NA
[7 empty] | 135 PREPARATION OF PUBLICATIONS | 0 | 0 | NA | 0 | 0 | 0 | NA